## Sheet1
ID | Description | Priority (1-5) | Status | Affected vi(s) | Comments
Issue_026 | Creating the label in the calling code causes an error 1055 | 5 | In Work | \Utility\Add Evaluation String.vi | It should be added as a free label if the Assert is outside the CDS, or as a subdiagram label if it is inside the CDS. Believe this should be fixed in build version 1.0.0.18. Checking now. Found multiple reasons all contributing. "\Utility\Rename Subdiagram Label.vi" is in the wrong place, it is located after the vi has been inlined and the vi reference is therefore invalid. "\Utility\Rename Subdiagram Label.vi" is also not finding the conditional disable structure correctly. Need to figure out the correct order of events, with the "Rename Subdiagram Label.vi" before deleting the outer vi, it fails in one configuration (outside/both) and the other way round it will fail in a different configuration.....
Issue_010 | Create new assert UI takes too long to load | 4 | Open | \Plugins\Utility\Build Assert VI.vi | When a new assert is being created, the UI has to load dependencies each time and takes several seconds to load up.
Issue_021 | Change "None" to "Display Only" in the failure actions enum | 4 | Open | \Core\Assert API Components\Failure Actions.ctl | May have downstream effects which also have to be sorted out
Issue_007 | Create new assert UI does not default to the correct state when launched, sometimes off to the side | 3 | Open | \Plugins\Utility\Build Assert VI.vi
Issue_009 | Pause Application does not pause on the right spot | 3 | Open | \Core\Assert API Components\Log Assert Core Components\Failure Actions\Pause Application\Action.vi
Issue_015 | Floating point numeric comparison precision is currently fixed | 3 | Open | \Plugins\Utility\Convert to scripting configuration.vi
Issue_025 | Change the templates to a single vim so changes to all can be easily applied | 3 | Open | \Plugins\Templates | Such as renaming the CDS
Issue_027 | Make sure the confirm wire reference process will work fully with nested structures. | 3 | Open | \Plugins\Utility\Confirm Wire Reference.vi | Build some unit tests to test if it will work first.
Issue_008 | Create assert memory tracking to shut down unused references | 2 | Open | \Core\Assert API Components\Log Assert Core Components\Event Transmission\Get Failure Action Event.vi | Currently just opens a new event for each assert and never shuts them down until the application is closed, memory leak (but a small one)
Issue_011 | Add the variant to data string function back to get data values added to the log file | 2 | Open | \Core\Assert API Components\Log Assert Core Components\Failure Actions\Log To File\Action.vi
Issue_012 | Only ever launch one instance of the dynamic filter window | 2 | Open | \Core\Main Display\Main Display\Launch Dynamic Filter Window.vi
Issue_013 | Add a UID to filters created so that the filter isn't overwritten if a new one is built with the same name | 2 | Open | \Core\Filter Config Display\Filter Config Display\Filter Dialog.vi
Issue_002 | Changes to "Inline or Forked.vi" broke calling code | 5 | Solved | \Plugins\Utility\Inline or Forked.vi | added in the code to translate the wire type to the new one required by the "Inline or Forked.vi". Now appears to be working.
Issue_004 | Asserts aren't being added to the wires correctly when inside a structure | 5 | Solved |  | I think its for both inline and forked asserts being added. When its inside a structure, the object reference is coming through as invalid.
Issue_016 | add an option to insert new assert vi's on a fork rather than inline. | 5 | Solved | \Plugins\Utility\Inline or Forked.vi
Issue_018 | Conditional disable is not deleted, no error | 5 | Solved | \Plugins\Utility\Delete CDS.vi | Does not generate an error - just doesn't do anything Turns out I was just being a dumbass!
Issue_019 | Case structure to pull forked/inline setting from config file is Inline in both cases in the main UK | 5 | Solved | \Plugins\Utility\Build Assert VI.vi
Issue_020 | Numeric constant type change vi is erroring when building asserts | 5 | Solved | \Utility\Changes Constant Types.vi | Turned out it was because I put a CDS around everything in the templates and wasn't scanning with the Tref by label function - I was doing that for other changes. Now updated the code and it will work better. Build 1.0.0.14
Issue_022 | Path for the CDS Structure vi is wrong | 5 | Solved | \Utility\CDS Placement Setup.vi | Change the relative path to "..\..\Templates\CDS Template\CDS Structure.vi"
Issue_023 | CDS in the templates is named different to the label searched for when deleting the CDS | 5 | Solved | \Utility\Delete CDS.vi | Either change all the templates to "CDS" or change the label being searched for to "Conditional Disable Structure". Make sure it matches the CDS name in "CDS Template\CDS Structure.vi"
Issue_024 | CDS is deleted during the edit time, but then the version called in the vi still contains it | 5 | Solved | \Utility\Delete CDS.vi | Something to do with the cache, not figured this one out yet - because the vi opens a new reference from file, its resaving the version on file rather than the version in memory. Change the "Save VI" functionality to gi the option of a reference or a file.
Issue_003 | Right click plugin isn't appearing | 4 | Solved
Issue_014 | Support multiple assert creation instead of just the first one in the array | 4 | Solved | \Plugins\RCF Code\edit time panel and diagram\Assert API.llb\Assert API.vi \Plugins\QD Code\Scripting Code\Create New Assert.vi \Plugins\RCF Code\edit time panel and diagram\Assert API.llb\Execute Assert API.vi
Issue_017 | Add CDS outside of the assert vi (potentially in addition to the one inside or with a config file option) | 4 | Solved | \Plugins\Utility\Full Build Assert.vi | I think this is getting close to being sorted now - need to test it and then fix all the crap that comes out….
Issue_001 | Useless naming of object references | 3 | Solved | \Plugins\Utility\Full Build Assert.vi \Plugins\Utility\Set Assert VI UID.vi \Plugins\Utility\Add Evaluation String
Issue_006 | Uninstallation of the package is not working well, the wrong components are attempted to be uninstalled from the LabVIEW Data directory | 3 | Solved | \VIP Build\Post-Uninstall Custom Action.vi | Now working nicely.
Issue_005 | Default to the main screen when the UI is started | 2 | Solved | \Core\Main Display\Main Display\Actor Core.vi | Solved by adding a simple local variable on startup for the tab control